## Logframe
Results Framework - Green Valley Livelihoods Programme (synthetic)
Level | Code | Result statement | Indicator | Unit | Baseline | Target | Means of verification | Frequency
Impact | 0 | Household incomes in the valley increased | Average monthly household income | JOD | 310 | 400 | Household survey | Annual
Outcome | 1 | Women's participation in agri-food production increased | Number of women completing agri-food training | people | 0 | 400 | Training attendance records | Quarterly
|  |  | % of trained women applying new practices | % | 0 | 60 | Follow-up survey | Semiannual
Output | 1.1 | Training courses delivered | Number of training sessions held | sessions | 0 | 80 | Session reports | Quarterly
Output | 1.2 | Start-up kits distributed | Number of start-up kits distributed | kits | 0 | 250 | Distribution lists | Quarterly
Outcome | 2 | Market access for small producers improved | Total sales through cooperative markets | JOD | 12000 | 50000 | Market sales records | Quarterly
Output | 2.1 | Cooperative market platform launched | Market platform operational | milestone | No | Yes | Project reports | Once
Assumption | Risk level
Security situation remains stable | Medium
Municipal partners keep co-funding | Low

## Notes (hidden)
Targets are end-of-programme values.

## Follow-up survey
Respondent ID | (open text)
Sex | Female Male
SECTION A - PRACTICES
1. Since the training, have you applied the new practices? | Yes, regularly Yes, sometimes No
2. Which practices have you applied? (Select all that apply) | Composting Drip irrigation Improved seeds Other
3. How many people in your household work on the farm? | Number: ____
SECTION B - CLOSING
4. Comments | (open text)

## Training attendance records
Participant ID
Participant name
Phone number
Sex | Female / Male
Session date