# Results Framework - Green Valley Livelihoods Programme (synthetic)

This monitoring plan describes how progress of the programme is measured. Indicators are reported quarterly unless stated otherwise.

## Indicators

| Level | Code | Result statement | Indicator | Unit | Baseline | Target | Means of verification | Frequency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact | 0 | Household incomes in the valley increased | Average monthly household income | JOD | 310 | 400 | Household survey | Annual |
| Outcome | 1 | Women's participation in agri-food production increased | Number of women completing agri-food training | people | 0 | 400 | Training attendance records | Quarterly |
| Outcome | 1 | Women's participation in agri-food production increased | % of trained women applying new practices | % | 0 | 60 | Follow-up survey | Semiannual |
| Output | 1.1 | Training courses delivered | Number of training sessions held | sessions | 0 | 80 | Session reports | Quarterly |
| Output | 1.2 | Start-up kits distributed | Number of start-up kits distributed | kits | 0 | 250 | Distribution lists | Quarterly |
| Outcome | 2 | Market access for small producers improved | Total sales through cooperative markets | JOD | 12000 | 50000 | Market sales records | Quarterly |
| Output | 2.1 | Cooperative market platform launched | Market platform operational | milestone | No | Yes | Project reports | Once |

## Assumptions

Security situation remains stable

Municipal partners keep co-funding